## APS112 Gantt Chart
PROJECT 095 GANTT CHART | [44 empty] | https://goo.gl/4UV8Cz
|  |  | COMMUNICATIONS REP | CHRIS YIP | RESEARCHER | ANJALI JAMMULAMADAKA
| PROJECT TITLE | SUSSEX CLUBHOUSE SPACE AUDIT | TEAM LEADER | LYDIA MESSIHA | SECRETARY | MARGARET CHEN
| PROJECT # | 95 | PROJECT MANAGER | MATTHEW TING | EDITOR | DORA LYU
|  | Assigned but will be reviewed with everyone during meeting |  |  |  | PHASE ONE | [19 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE THREE
TASK ID | TASK TITLE | TASK OWNER | DURATION OF TASK | Predecessors | PCT OF TASK COMPLETE | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.0 | Client Email | Everyone |  |  | 100% | bar: WEEK 3 M to WEEK 3 F
2.0 | Team Charter | Everyone | 5hr |  | 100% | bar: WEEK 3 F to WEEK 4 M
3.0 | Client Meeting Plan |  | 6hr |  | 100%
3.1 | Introductions | everyone | 1 min |  | 100% | bar: WEEK 4 W
3.2 | Audience Assessment | Researcher, Editor | 2hr |  | 100% | bar: WEEK 4 W
3.3 | Client Questions | Leader, Secretary | 2hr |  | 100% | bar: WEEK 4 W
3.4 | Strategies | Comm.rep, Proj manager | 1 hr |  | 100% | bar: WEEK 4 W
3.5 | Close of meeting | everyone | 5 min |  | 100% | bar: WEEK 4 W
4.0 | Status report #1 | Comm.rep | 1 hr | 3 | 100% | bar: WEEK 4 F to WEEK 5 W
5.0 | Project Requirements |  | 10hr |  | 100% | bar: WEEK 4 F to WEEK 6 F
5.1 | Functions | Proj manager | 2hr |  | 100% | bar: WEEK 5 W to WEEK 6 T
5.2 | Objectives | Leader | 2hr |  | 100% | bar: WEEK 5 W to WEEK 6 T
5.3 | Constraints | Researcher | 2hr |  | 100% | bar: WEEK 5 W to WEEK 6 T
5.4 | Service Environment | Secretary | 2hr |  | 100% | bar: WEEK 5 W to WEEK 6 T
5.5 | Stakeholders | Editor | 2hr |  | 100% | bar: WEEK 5 W to WEEK 6 T
5.6 | Problem Statement | Comm.rep | 2hr |  | 100% | bar: WEEK 5 W to WEEK 6 T
5.7 | Executive summary | Everyone | 2hr |  | 100% | bar: WEEK 6 T to WEEK 6 W
5.8 | Introductions | Everyone | 1hr |  | 100% | bar: WEEK 6 T to WEEK 6 W
6.0 | Status report #2 | Secretary | 2hr | 5 | 100% | bar: WEEK 6 T to WEEK 6 W
7.0 | Conceptual Design Specifications |  | 20hr |  | 100% | bar: WEEK 7 R to WEEK 12 M
7.1 | Benchmarking: Hart House | Leader and Researcher | 2hr |  | 100% | bar: WEEK 7 R to WEEK 8 F
7.2 | Benchmarking: Gernstein library | Proj Manager | 2hr |  | 100% | bar: WEEK 7 R to WEEK 8 F
7.3 | Benchmarking: Myhal | Secretary and Editor | 2hr |  | 100% | bar: WEEK 7 R to WEEK 8 F
7.4 | Benchmarking: Dry Cleaning | Proj Manager and Editor | 2hr |  | 100% | bar: WEEK 7 R to WEEK 8 F
7.6 | Idea generation | Everyone | 5hr | 7.1-7.5 | 100% | bar: WEEK 9 M to WEEK 9 F
7.7 | PR Summary | Leader, Researcher |  | 5 | 100% | bar: WEEK 8 W to WEEK 8 F
7.8 | Alternative designs | 3 ppl |  |  | 100% | bar: WEEK 11 T to WEEK 11 R
7.9 | SCAMPER table | Everyone |  |  | 100% | bar: WEEK 9 M to WEEK 9 W
7.10 | Morph Chart | Everyone |  |  | 100% | bar: WEEK 9 W to WEEK 9 R
7.11 | Feasibility Chart | Everyone |  |  | 100% | bar: WEEK 10 R to WEEK 10 F
7.12 | Multi-voting | Everyone |  |  | 100% | bar: WEEK 10 F to WEEK 11 M
7.13 | Weighted decision matrix | Everyone |  |  | 100% | bar: WEEK 11 T to WEEK 11 W
7.14 | Alternate design selection process | Editor, Comm. Rep, Proj. Manager |  |  | 100% | bar: WEEK 11 T to WEEK 11 W
7.15 | Final design specifications | Everyone |  |  | 100% | bar: WEEK 11 T to WEEK 11 R
7.16 | Measures of Success | Comm. Rep |  |  | 100% | bar: WEEK 11 T to WEEK 11 R
7.17 | Executive Summary | Leader, Researcher |  |  | 100% | bar: WEEK 11 R to WEEK 12 M
7.18 | Introduction | Everyone |  |  | 100% | bar: WEEK 11 F to WEEK 12 M
7.19 | Conclusion | Everyone |  |  | 100% | bar: WEEK 11 F to WEEK 12 M
7.20 | Prototype | Proj Manager |  |  | 100% | bar: WEEK 8 T to WEEK 11 T
8.0 | Status Report #3 | Proj Manager |  |  | 100% | bar: WEEK 8 T to WEEK 8 W
9.0 | Design Review Gateway | Everyone |  |  | 100% | bar: WEEK 9 W to WEEK 10 W
10.0 | Status Report #4 | Leader |  |  | 100% | bar: WEEK 9 T to WEEK 9 W
11.0 | Status Report #5 | Researcher |  |  | 100% | bar: WEEK 11 T to WEEK 11 W
12.0 | Status Report #6 | Editor |  |  | 100% | bar: WEEK 12 T to WEEK 12 W
13.0 | FInal presentation | Everyone |  |  | 100% | bar: WEEK 13 M to WEEK 15 T
13.1 | CDS revision | Everyone |  |  | 0% | bar: WEEK 13 R to WEEK 13 F
13.2 |  |  |  |  | 0%
13.3 |  |  |  |  | 0%
13.4 |  |  |  |  | 0%
13.5 |  |  |  |  | 0%
13.6 |  |  |  |  | 0%
13.7 |  |  |  |  | 0%
13.8 |  |  |  |  | 0%
13.9 |  |  |  |  | 0%

## Assignment overview
Client Email | Team | In tutorial. Week of January 22
Team Charter (TC) 1 | Team | 2024-01-29 11:59
Client Meeting Plan | Team | In tutorial. Week of January 29
Preliminary Literature Review (PLR) | Individual | 2024-02-05 11:59
Status Report 1 & 2 | Team | In tutorial. Week of February 5 and 12
Project Requirements (PR) | Team | 2024-02-16 23:59
Peer Evaluation 1 | Individual | 2024-02-26 11:59
Status Report 3 & 4 | Team | In tutorial. Week of February 26 and March 4
Team Charter 2 | Team | In tutorial. Week of March 4
Design Review Gateway Presentation (DRG) | Team | In tutorial, week of March 11
Status Report 5 | Team | In tutorial. Week of March 18
Conceptual Design Specification (CDS) | Team | 2024-03-25 11:59
Midterm | Individual | Tuesday, March 26, 2024 1-3 PM
Peer Evaluation 2 | Individual | 2024-04-01 11:59
Status Report 6 | Team | In tutorial. Week of April 1
Team Role Observation and Analysis (TROA) | Individual | 2024-04-08 11:59
Performance Review | Individual | Ongoing
Final Presentation | Team | TBD